## Instruction Sheet
EFI Group- Cost Estimating Template Purpose and Instructions
PURPOSE: EFI Group has developed a Cost Estimating Template to ensure consistent application of the Best Practice Techniques from our experience. This template includes both mandatory and open line items for Project Managers to use when estimating project. EFI Group uses this same template for every phase of project development from Preliminary Engineering through Cost Tracking for Project Implementation.
Section Number | Section Description | Instructions and Features
100 | Site Preparation, Buildings, Structures and Foundations | List all known installation items that are part of Civil, Structural and Architectural design (CSA Design) for the project. Most often we will include BOTH the installation costs and the purchased material costs in this section of the spreadsheet.
Line Item Contingency | Applies to ALL Direct Cost Sections | The Line Item Contingency (LOC) is a special feature of all direct cost items, sections 100 through 800. The purpose of LOC is to mitigate risk for price increases on a specific line Item. As a starting point, we normally show 15% as LOC. As more cost information is known within each project group, we will lower the percentage.
200 | Process Equipment (purchase ONLY) | All equipment that is used in the process is listed here. Sometimes for large projects, we will include a separate equipment list spreadsheet and transfer a summary of costs here.
300 | Support Equipment (Purchase ONLY) | Support equipment is often overlooked when estimating projects. We include a separate section to capture costs for this equipment. Typical examples of support equipment include: air compressors, maintenance cranes, special tools, mobile equipment, etc.
400 | Installation of Mechanical Equipment | Cost estimates for all mechanical construction costs are detailed in this section. This includes the installation of process and support equipment. Also included is all piping associated with the project.
500 | Electrical Power Supply Equipment (Purchase ONLY) | Line items associated with power supply equipment are listed here including: substations, transformers, MCC's, power panels, etc. Sometimes light fixtures are also included here, but can also be shown as a single installation Item in Section 700.
600 | Controls Related Equipment (Purchase ONLY) | Controls related equipment are shown in this section including: PLC's, HMI's, control panels, instrumentation, etc. Note: Often a separate instrumentation list is prepared, transferring the total costs for the instrumentation package onto a single line item on the Cost Estimate template.
700 | Electrical Power & Controls Installation | Contractor labor and tools associated with the installation of power systems and controls are listed here. Installation bulk items (conduct, wire, local receptacles, switches, etc.) are grouped in this section. We would normally include here all bulk items that are part of the Construction Scope of Work.
800 | Miscellaneous | We use the "Miscellaneous" section to capture additional costs associated with direct costs that are not specifically mentioned in the sections above. See the template for the basic listing. The Project Manager can also include other items that are important to their project in this line item.
900 | Indirect Costs | Indirect Cost are project costs that are not part of a fixed asset. Listed on the Cost Estimating Template are the Indirect Costs that we typically include on projects.
999 | Final Project Contingency | Final Project Contingency is for a totally different purpose than Line Item Contingency. During the course of design or construction, NEW information and cost items arise that were not part of the original budget. Including Final Project Contingency mitigates the risk of cost items that WERE NOT identified during the original project planning and preliminary engineering. Typically, we will begin with 25% early in preliminary engineering and gradually reduce through the capital cost development activities. The lowest Final Project Contingency is 10%.
Contingency: Used to guard against project risk |  | We consider two types of risk when determining a level of contingency for a project: Price Risk and Scope of Work Risk. Below is a definition of each type of risk:
Price Risk: Involves the cost for equipment or services that have been identified in the project’s Scope of Work. For example, the Actual Cost for equipment will be different (+/-) than Budget Cost determined during the Preliminary Engineering development. The same applies to actual costs for engineering or installation services. Line Item Contingency covers increases in costs between Actual Cost vs. Budget Cost of items that have been identified to be in the project’s overall scope.
Scope of Work (SOW) Risk: Involves changes that occur during the Implementation Phase of the project. These are equipment needs and additional engineering and installation requirements that were not specifically identified during the Project Development Process. For example, the relocation of an underground pipe that was not discovered during preliminary engineering, and is not included in the detailed Project Cost Estimate. In short, SOW Contingency covers unforeseen events that occur during installation and commissioning.
The amount of Total Contingency assigned to a project varies based on the completeness of preliminary engineering and the accuracy of cost information available during the development of the Cost Estimate.
410.368.5101 / www.efigroupllc.com

## Cost Estimate Template
Process Line # | Item # | Description | Quantity | Units | Specifications | Motor Hp | Item Weight | Vendor Information | Unit Cost | Extended Cost | Quoted Price? | Lead Time | PO's Issued | Anticipated Variance | Anticipated Actual | Responsibility | Comments
[6 empty] | Hp | Lbs |  | USD | USD | Y/N | Wks | Y/N | USD | USD
Building Modifications and Additions | 100
| 101 | Process Building | 1 | Lot | Building Specification BLDG-01 |  |  |  | 25000 | 25000 |  |  |  |  | 25000
| 102 | [8 empty] | 0 |  |  |  |  | 0
| 103 | [8 empty] | 0 |  |  |  |  | 0
| 104 | [8 empty] | 0 |  |  |  |  | 0
| 199 | Line Item Contingency | 15% | [6 empty] | 3750 |  |  |  |  | 3750
[8 empty] | Sub-Total |  | 28750 |  |  |  |  | 28750
0
Process Equipment | 200
| 201 | Equipment Item 1 | 1 | Each | Spec # EQ-01 |  |  |  | 20000 | 20000 |  |  |  |  | 20000
| 202 | Equipment Item 2 | 5 | Each | Spec # EQ-02 |  |  |  | 5000 | 25000 |  |  |  |  | 25000
| 203 | [8 empty] | 0 |  |  |  |  | 0
| 204 | [8 empty] | 0 |  |  |  |  | 0
| 205 | [8 empty] | 0
` | 299 | Line Item Contingency | 15% | [6 empty] | 6750 |  |  |  |  | 6750
[8 empty] | Sub-Total |  | 51750 |  |  |  |  | 51750
0
Support Equipment | 300 | NONE REQUIRED
[Purchase ONLY] | 301 | [8 empty] | 0 |  |  |  |  | 0
| 302 | [8 empty] | 0 |  |  |  |  | 0
| 303 | [8 empty] | 0
| 304 | [8 empty] | 0
| 305 | [8 empty] | 0
| 399 | Line Item Contingency | 15% | [6 empty] | 0 |  |  |  |  | 0
[8 empty] | Sub-Total |  | 0 |  |  |  |  | 0
0
Mechanical Installation Details | 400 | [8 empty] | 0 |  |  |  |  | 0
| 401 | Total Mechical Installation | 1 | Lot | Contractor Bid Specification #M-1 |  |  | ABC Contracting |  | 50000 |  |  |  |  | 50000
| 402 | [8 empty] | 0 |  |  |  |  | 0
| 403 | [8 empty] | 0 |  |  |  |  | 0
| 404 | [8 empty] | 0 |  |  |  |  | 0
| 405 | [8 empty] | 0 |  |  |  |  | 0
| 499 | Line Item Contingency | 15% | [6 empty] | 7500 |  |  |  |  | 7500
[8 empty] | Sub-Total |  | 57500 |  |  |  |  | 57500
0
Electrical Power Supply Equipment | 500 | [8 empty] | 0 |  |  |  |  | 0
Purchase ONLY | 501 | Motor Control Center | 1 | Each |  |  |  |  | 20000 | 20000 |  |  |  |  | 20000
| 502 | [8 empty] | 0 |  |  |  |  | 0
| 503 | [8 empty] | 0 |  |  |  |  | 0
| 504 | [8 empty] | 0 |  |  |  |  | 0
| 599 | Line Item Contingency | 15% | [6 empty] | 3000 |  |  |  |  | 3000
[8 empty] | Sub-Total |  | 23000 |  |  |  |  | 23000
0
Controls related equipment | 600 | [8 empty] | 0 |  |  |  |  | 0
Purchase ONLY | 601 | Controls Equipment Package | 1 | Lot |  |  |  |  | 15000 | 15000 |  |  |  |  | 15000
| 602 | [8 empty] | 0 |  |  |  |  | 0
| 603 | [8 empty] | 0 |  |  |  |  | 0
| 604 | [8 empty] | 0 |  |  |  |  | 0
| 699 | Line Item Contingency | 15% | [6 empty] | 2250 |  |  |  |  | 2250
[8 empty] | Sub-Total |  | 17250 |  |  |  |  | 17250
0
Electrical Power & Controls Installation | 700 | [8 empty] | 0 |  |  |  |  | 0
| 701 | Power and Controls Bid | 1 | Lot | Contractor Bid Specification #P&C-01 |  |  |  | 25000 | 25000 |  |  |  |  | 25000
| 702 | [8 empty] | 0 |  |  |  |  | 0
| 703 | [8 empty] | 0 |  |  |  |  | 0
| 704 | [8 empty] | 0 |  |  |  |  | 0
| 799 | Line Item Contingency | 15% | [6 empty] | 3750 |  |  |  |  | 3750
[8 empty] | Sub-Total |  | 28750 |  |  |  |  | 28750
0
Miscellaneous | 800
| 801 | Freight on purchased equipment | 3% |  | Assumed 3% of purchased equipment |  |  |  |  | 2760 |  |  |  |  | 2760
| 802 | Import tarriff on foreign equipment | [5 empty] | NONE |  | 0 |  |  |  |  | 0
| 803 | Exisiting equipment demolition | 1 | Lot |  |  |  |  | 9000 | 9000 |  |  |  |  | 9000
| 804 | Miscellaneous repairs | [5 empty] | NONE |  | 0 |  |  |  |  | 0
| 805 | Relocation of equipment and utilities | [5 empty] | NONE |  | 0 |  |  |  |  | 0
| 806 | Start-up assistance - process equipment | 1 | Lot | For Equipment Item #1 |  |  |  | 1000 | 1000 |  |  |  |  | 1000
| 807 | Start-up assistance - controls |  |  | Included in Cost Item E-930 |  |  |  |  | 0 |  |  |  |  | 0
| 808 | Critical spare parts | 10% |  | ALLOWANCE FOR SPARES AT 10% |  |  |  |  | 9200 |  |  |  |  | 9200
| 809 | <Other Miscellaneous Direct Costs> | [5 empty] | NONE
| 899 | Line Item Contingency | 15% | [6 empty] | 3294 |  |  |  |  | 3294
[8 empty] | Sub-Total |  | 25254 |  |  |  |  | 25254
FINAL ESTIMATE DETAILS for DIRECT COSTS | Sub-total | Total cost of the equipment, installation and bulk items | [7 empty] | 232254 |  |  |  |  | 232254
Indirect Cost Items | 900
| E-901 | Preliminary Engineering | [5 empty] | EFI Group, LLC |  | 9000 |  |  |  |  | 9000
| E-910 | Detailed Design Engineering (including construction documents and project documentation) | 10% |  | ALLOWANCE FOR ENGINEERING |  |  |  |  | 23225.4 |  |  |  |  | 23225.4
| E-920 | Engineering Construction Support (including shop drawing review, installation technical support) |  |  | Included in Item E-910 |  |  |  |  | 0 |  |  |  |  | 0
| E-921 | Record Drawings (Using Construction Red-lines) |  |  | Included in Item E-910 |  |  |  |  | 0 |  |  |  |  | 0
| E-922 | Project Close Out Costs | [5 empty] | BY CLIENT |  | 0 |  |  |  |  | 0
| E-930 | PLC Controls Engineering and System Integration | 1 | Lot |  |  |  | plc Controls, Inc. | 19000 | 19000 |  |  |  |  | 19000
| HSE-940 | Health, Safety and Environmental Permitting and Consulting | [5 empty] | BY CLIENT |  | 0 |  |  |  |  | 0
| PM-950 | Project Management Support | [5 empty] | BY CLIENT |  | 0 |  |  |  |  | 0
| CM-960 | Construction Management | [5 empty] | BY CLIENT |  | 0 |  |  |  |  | 0
| INT-970 | Capitalized Interest | [5 empty] | NONE |  | 0 |  |  |  |  | 0
| X-980 | <Other Indirects> | [5 empty] | NONE |  | 0 |  |  |  |  | 0
| 990 | Total Project Contingency Sub-Total | 25% | [6 empty] | 70869.85 |  |  |  |  | 70869.85 |  | Contingencies are calculated in each section. This cell is for reference only and is not included in the Total Project Cost.
Total Project Cost | [9 empty] | 354349.25 |  |  | 0 | 0 | 283479.4

## Closing
EFI Group- Cost Estimating Template Thank You!
Thank you for downloading EFI Group’s Cost Estimate Template for Mitigating Project Risk.
We hope you found the instructions and the template itself valuable and, from our experience, we know it will serve you well in minimizing the financial and technical risk in your projects going forward.
We will check in with you in a week or so to see if you have any questions, as well as send you periodic resources we think you’ll find valuable.
Our role in industry is to help manufacturers like you make key improvements of all kinds for increased profitability, using our unique approach that minimizes risk.
No matter where your company is now, we’d very much value the opportunity to talk with you about increasing your success and we believe the conversation will be well worth your time.
To schedule a complimentary conversation with EFI Group’s leadership team, email Jim Solich at jsolich@efigroupllc.com. Again, we will check in with you as well to personally see if we can be of further assistance.
410.368.5101 / www.efigroupllc.com