|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Committee/Task Force:** | Data Sharing & Mapping | | | | | |
| **Date of Meeting:**  (MM/DD/YYYY) | 06/22/2017 | | **Time:** | | 3:00P-4:30P | |
| **Minutes Prepared By:** | Ruth Reichard | | **Location:** | | 30 South Meridian Street, Room 9003, Indianapolis, IN 46204 | |
| **1. Meeting Objective(s)** | | | | | | |
| Obtain results of survey of task forces’ & committees’ data needs; update on status of MOU collections; update on ISG; obtain a report on progress of MPH & INK merger. | | | | | | |
| **2. Standing Members** | | | | | | |
| **Name** | | **Organization** | | | | **In Attendance (X indicates present)** |
| Julie Whitman, Chair | | Indiana Youth Institute | | | | **X** |
| Ashley Aiken | | Indiana Criminal Justice Institute | | | | **X** |
| Tony Barker | | Indiana Office of Technology | | | |  |
| Sirrilla Blackmon | | Division of Mental Health & Addiction | | | |  |
| Michael Commons | | IOCS | | | | **X** |
| Mary DePrez | | Trial Court Technology | | | |  |
| Matthew Hagenbush | | IOCS | | | | **X** |
| Leah Hemze-Mills | | Department of Child Services | | | |  |
| Jeff Hudnall | | Indiana Network of Knowledge | | | | **Joined via telephone** |
| Devon McDonald | | Indiana Criminal Justice Institute | | | |  |
| David Murtaugh | | Indiana Criminal Justice Institute | | | |  |
| Dewand Neely | | Indiana Office of Technology | | | |  |
| Sarah Schelle | | Department of Correction | | | |  |
| Barbara Seitz de Martinez | | Indiana Prevention Resource Center | | | | **Joined via telephone** |
| Susan Smith | | Casey Family Programs | | | |  |
| Lisa Thompson | | Trial Court Technology | | | | **X** |
| Doris Tolliver | | Department of Child Services | | | |  |
| Don Travis | | Department of Child Services | | | |  |
| Tamara Weaver | | Office of the Attorney General | | | | **Emily Crisler attended for TW** |
| **3. Staff/Guests** | | | | | | |
| **Name** | | **Organization** | | | | |
| Ruth Reichard | | IOCS | | | | |
| **4. Updates/Old Business** | | | | | | |
| **Topic** | **Main Points** | | | **Recommendations/Decisions** | | |
| **Approval of minutes from**  **previous meeting** |  | | | Approved by consensus. | | |
| **Update on status of action items from previous meeting** | All action items from the 4/27/17 meeting minutes have been accomplished, with the exception of the item related to the IYI newsletter. | | | This will be a standing agenda item from now on. | | |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Committee/Task Force:** | Data Sharing & Mapping | | | |
| **Date of Meeting:**  (MM/DD/YYYY) | 06/22/2017 | **Time:** | | 3:00P-4:30P |
| **Minutes Prepared By:** | Ruth Reichard | **Location:** | | 30 South Meridian Street, Room 9003, Indianapolis, IN 46204 |
| **Update on Capstone Project/ISG** | * Lisa Thompson reported on the 5/1-6/1 metrics for the mobile application. * Michael Commons reported on plans to update the white paper and then the app, as well as to re-survey constituents to measure whether the ISG is making a positive difference. * Matt Hagenbush raised the issue of who “owns” this project and is thus responsible for the labor associated with it, noting that staff leadership at the courts believes the Committee should own the project. | | * Lisa/TCT will prepare a one-page summary of the metrics for each Committee meeting. We will use the projector in the room to view as a group. * We will probably use the same survey questions as we did in 2015, but add questions about the white paper’s & app’s efficacy. * We will reach out to the same attorney partners for the legal update process, and send the updated sections to the AG’s office for vetting before finalizing the white paper and app. * We may add tiles/paths to the app for the child’s JD attorney (as part of the IPDC’s OJJDP grant) & for foster parents. * Regarding the division of labor/responsibility/ownership of the ISG, after discussion we decided that MOUs with member agencies may be necessary. | |
| **5. New Business/Presentations** | | | | |
| **Topic** | **Main Points** | | **Recommendations/Decisions** | |
| **Update on MPH/INK** | Jeff Hudnall gave a report on the practical effect of the passage of HEA 1470, which merged INK & MPH. INK will be a program within MPH & the director of MPH will be the Chief Data Officer. INK will become EWD (Education & Workforce Development). It should be possible to combine EWD data with other agencies’ data to enhance analysis. MPH will collaborate with agencies for analytics and help inform policies with data. | | Jeff will reach out to Darshan Shah, head of MPH, to set up a meeting with Julie to discuss his joining the committee and the possibiltiy of presenting to the Commission.. | |
| **Report on Survey of Task Forces’ & Committees’ Data Needs** | Julie Whitman surveyed all task forces & committees. The only request for data came from the Educational Outcomes Task Force, which would like data on educational outcomes of system-involved youth. We discussed how to achieve this. All agreed it would be ideal for Darshan and Julie to present to the Commission on how MPH could be used to answer this question, and ask the Commission to support an  information-sharing agreement among the relevant agencies (DOE, DCS, Courts). | | Jeff will ask Darshan to meet with Julie to discuss his possible role on the Committee as well as a potential presentation to the Commission. | |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Committee/Task Force:** | Data Sharing & Mapping | | | |
| **Date of Meeting:**  (MM/DD/YYYY) | 06/22/2017 | **Time:** | | 3:00P-4:30P |
| **Minutes Prepared By:** | Ruth Reichard | **Location:** | | 30 South Meridian Street, Room 9003, Indianapolis, IN 46204 |
| **Update from MOU Subcommittee** | Ashley Aiken reported that she & Tamara Weaver met and reviewed 5 sample MOUs; all were good, and all were different--there was no one perfect template that would fit all situations/agencies.  They compiled a list of key points to be included in any data-sharing MOU. | | Committee members need to review the model MOUs. Ashley will draft a list of essential elements of information-sharing MOUs. We may link to that document in the drop-down menu of the ISG app under “best practices.” | |
| **(Not on the agenda) Membership** | Julie Whitman observed that our membership should contain the data/information systems personnel from each member agency. This would mean someone new representing DMHA, and also filling a gap from DOE. We will wait until we have a specific data need before re-inviting someone from ISDH. | | Julie will reach out to John Keller, Chief Technology Officer for DOE, to identify the correct staff member.  Julie will contact Sirrilla Blackmon about the most appropriate staff member from DMHA. | |

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Committee/Task Force:** | | Data Sharing & Mapping | | | | | | | | |
| **Date of Meeting:**  (MM/DD/YYYY) | | 06/22/2017 | | | **Time:** | | | 3:00P-4:30P | | |
| **Minutes Prepared By:** | | Ruth Reichard | | | **Location:** | | | 30 South Meridian Street, Room 9003, Indianapolis, IN 46204 | | |
| **6. Action Items (Include recommendations/queries for Executive Committee)** | | | | | | | | | | |
| **Action** |  |  |  |  |  |  | **Responsibility** | |  | **Due Date** |
| Check if ISG has been mentioned in the IYI newsletter. | | | | | | | Julie Whitman | | | August 3, 2017 |
| Make list of who should be the ISG partners & what the roles & responsibilities of each partner should be, including with what frequency these roles/responsibilities will be performed. This will be the basis of the MOUs we hope to draft clarifying  the “ownership” of the ISG, white paper, & mobile app. | | | | | | | Michael Commons | | | Mid-July 2017 |
| Schedule a meeting to discuss a timeline for updating the white paper & app. | | | | | | | Michael Commons | | | Mid-July 2017 |
| Send sample MOUs to Ruth, for distribution to entire committee membership. | | | | | | | Ashley Aiken | | | Mid-July 2017 |
| Review sample MOUs before next meeting. | | | | | | | All members. | | | August 3, 2017 |
| Draft “MOU essential elements” document. | | | | | | | Ashley Aiken | | | August 3, 2017 |
| Speak with Darshan Shah & set up meeting with Julie. | | | | | | | Jeff Hudnall | | | July 24, 2017 |
| Contact DMHA & DOE about appropriate staff members for our Committee. | | | | | | | Julie Whitman | | | July 24, 2017 |
| **7. Adjournment** | | | | | | | | | | |
| **Action** |  |  |  |  |  |  |  |  |  | **Time** |
| Meeting adjourned. | | | | | | | | | | 4:17P |
| **8. Next Meeting** | | | | | | | | | | |
| **Date:** (MM/DD/YYYY) | 08/03/2017 | | **Time:** | 3:00-4:30P | | **Location:** | | | 30 S. Meridian Street, Suite 500 Atrium Conference Room, Indianapolis, IN 46204 | |
| **Topics/Objective(s):** | Update on ISG. Update on MOU project. Update on MPH. Explore possible means of obtaining data on educational outcomes of system-involved youth. | | | | | | | | | |