# Research Grant Proposals-Sample Sections Project Schedule – 4 examples from prior proposals: Example 1:

| TASK | TARGET COMPLETION DATE |
| --- | --- |
| Phase I |  |
| 1. IRB Submission | completed |
| 2. IRB Approval | 06-01-07 |
| 3. Interview Questions Finalized | 08-01-07 |
| 4. Schedule Interviews | 09-01-07 |
| 5. Data Collection | 10-15-07 |
| 6. Transcribe Interviews | 11-15-07 |
| 7. Write-up Findings | 01-15-07 |
| Phase II |  |
| 8. Develop Surveys | 01-30-08 |
| 9. Finalize Organizational Sample | 12-01-07 |
| 10. Data Collection – Part 2 (organizational sample) | 03-15-08 |
| 11. Data Cleaning | 04-30-08 |
| 12. Data Analysis | 06-15-08 |
| 13. Write Up Findings | 08-01-08 |
| 14. Submit to Academy of Management Conference | 12-01-08 |
| 15. Submit to Academy of Management Journal and Human Resource Management Journal | 09-01-09 |

| Year | Research activity | Target Dates |
| --- | --- | --- |
| Phase | Complete IRB approval process (4/07-5/07) | 5/07 |
| 1: | Finalize interview protocol | 8/07 |
| 2007 | Conduct 45 interview sessions (8/07-1/08) | 1/08 |
| to | Content analysis of interview sessions (10/07-3/08) | 3/08 |
| 2008 | Make final decisions regarding survey measures | 10/07 |
|  | Write conference submission on qualitative results to date – AOM | 1/08 |
|  | Use interview results to fine-tune online survey protocol (10/07-3/08) | 3/08 |
|  | Create online survey (beginning 10/07) | 4/08 |
|  | Confirm survey participants (1/08-4/08) | 4/08 |
|  | Administer online survey (5/08-6/08) | 6/08 |
|  | Write and submit article on qualitative results (3/08-8/08) | 8/08 |
| Phase | Analyze quantitative results from surveys (7/08-9/08) | 9/08 |
| 2: | Write and submit conference paper on quantitative survey results – AOM | 1/09 |
| 2008 | (10/08-1/09) | 1/09 |
| to | Write and submit conference paper on quantitative and qualitative results – | 3/09 |
| 2009 | AIB | 4/09 |
|  | Prepare executive summary for participants and their firms | 5/09 |
|  | Write and submit article on final results (both quantitative and qualitative) | 7/09 |
|  | (10/08-4/09) |  |
|  | Submit final report to SHRM Foundation |  |
|  | Write and submit practitioner article (4/09-7/09) |  |

The proposed research will be completed in five phases over the two-year project period. Specifically, the following schedule is planned, assuming a start date on or about November 1, 2007:

| TASK | TARGET COMPLETION DATE |
| --- | --- |
| Phase I |  |
| 1. IRB Submission | 9-28-07 |
| 2. IRB Approval | 10-15-07 |
| 3. Pilot Testing of Time 1 Field Survey Completed | 11-30-07 |
| 4. Pilot Testing of Retiree Survey Completed | 11-30-07 |
| 5. Informational meetings with Out-of-State HR Directors Completed; Sample contact information obtained | 1-15-08 |
| Phase II |  |
| 6. Mail administration of Time 1 Field Survey | 02-22-08 |
| 7. Mail administration of Retiree Field Survey | 02-29-08 |
| 8. Participant reminders sent | 04-04-08 |
| Phase III |  |
| 9. Data coding and cleaning - Time 1 Field Survey | 06-13-08 |
| 10. Data coding and cleaning – Retiree Field Survey | 06-27-08 |
| 11. Data Analysis of Time 1 Field Survey and Retiree Field Survey | 08-29-08 |
| Phase IV |  |
| 12. Pilot testing of Time 2 Field Survey completed | 10-31-08 |
| 13. Write up and submit Retiree Survey findings to Academy of Management Conference, Human Resource Management Journal | 01-01-09 |
| 14. Mail administration of Time 2 Field Survey | 02-06-09 |
| 15. Archival data on employee status obtained from organizational records | 03-20-09 |
| 16. Data coding and cleaning – Time 2 Field Survey and archival data | 05-08-09 |
| 17. Data analysis of combined wave Field Surveys | 07-03-09 |
| Phase V |  |
| 18. Write up Field Survey findings and submit to SIOP Conference | 09-01-09 |
| 19. Submit Field Survey findings to Journal of Applied Psychology | 10-01-09 |
| 20. Write up executive summary; present results to organization; submit summary to Academy of Management Executive | 11-01-09 |

| Task | Targeted completion date |
| --- | --- |
| 1. Literature review and model development | Completed |
| 2. IRB approval (see Appendix) | Completed |
| 3. Identification and definition of life domains | Completed |
| 4. Generation of items (and gathering of other measures) | Completed |
| 5. Pilot testing of measure | Completed |
| 6. Development of web-based measure and functional testing | Completed |
| 7. Drawing of sample | 8-15-08 |
| 8. Emailing participants (in waves until desired sample obtained) | 8-30-08 |
| 9. Data collection | 10-15-08 |
| 10. Data cleaning | 11-15-08 |
| 11. Data analysis | 1-15-09 |
| 12. Generation of initial reports and conference submissions | 3-15-09 |
| 13. Development of pieces for dissemination to HR audiences | 6-1-09 |
| 14. Development of submissions for academic journals | 8-1-09 |